## Sheet1
ML API & Deployment Project Plan
2023
Notes: This is a fictional plan for the CI/CD Project if it were more complex. Difficulty scale: 1 (easiest) to 5 (hardest)
Q1 | Phase: ML API Development
Week Number | Start Date | Sprint | Difficulty | Feature/Goal | Status
1 | 2023-01-07 | 1 | 1 | Analysis, planning and understanding requirements | Done
2 | 2023-01-14
3 | 2023-01-21 | 2 | 2 | Collect and clean boston housing dataset | Done
4 | 2023-01-28
5 | 2023-02-04 | 3 | 5 | Create ML house price prediction engine with sklearn | Done
6 | 2023-02-11
7 | 2023-02-18 | 4 | 3 | Validate & test ML engine | Done
8 | 2023-02-25
9 | 2023-03-04 | 5 | 3 | Wrap ML engine into flask api | Done
10 | 2023-03-11
11 | 2023-03-18 | 6 | 2 | QA & Documentation | Done
12 | 2023-03-25
Overall Quarterly Goals
Create an ML API to predict house prices in the boston area.
Q2 | Phase: Deployment with CI/CD
Week Number | Start Date | Sprint | Difficulty | Feature/Goal | Status
13 | 2023-04-01 | 7 | 1 | Analysis, planning and understanding requirements | Done
14 | 2023-04-08
15 | 2023-04-15 | 8 | 3 | Deployment to Azure | Done
16 | 2023-04-22
17 | 2023-04-29 | 9 | 2 | Test ML API inc. load balancing | Done
18 | 2023-05-06
19 | 2023-05-13 | 10 | 3 | Basic CI/CD pipeline via Azure pipelines and github | In progress
20 | 2023-05-20
21 | 2023-05-27 | 11 | 4 | Custom CI/CD pipeline with tests, logging and alerts | Not started
22 | 2023-06-03
23 | 2023-06-10 | 12 | 2 | QA & Documentation | Not started
24 | 2023-06-17
Overall Quarterly Goals
Deploy the ML API | On Azure
Implement CI/CD | With Azure pipelines connected to github repository
Formulas:
Start Date = [Start Date, row below]-7
Start Date = [Start Date, row above]+7